## Weekly Status
Consultant Weekly Status — AutoLoan-DocIntel (14-day take-home)
Example rows are shaded — overwrite with your cohort. RAG/Tier are dropdowns; Due & Pass compute. Fill commits from consultant_status.py.
Identity |  |  |  |  | Week 1 check (Days 1-7) |  |  |  |  | Week 2 check (Days 8-14) |  |  |  |  | Final
Consultant | Branch | Start | Due (+14d) | Reviewer | W1 date | W1 RAG | W1 % | W1 commits | W1 notes | W2 date | W2 RAG | W2 % | W2 commits | W2 notes | Tier reached | Score /100 | Pass? | Recommendation
Alice Okafor | solution/alice | 2026-07-01 |  | R. Mehta | 2026-07-01 | Green | 100% | 9 | MUST slice done on time |  | Green | 80% | 11 | RAG+underwriting in; API in progress | Target | 82 |  | Advance — strong senior signal
Bob Nguyen | solution/bob | 2026-07-01 |  | R. Mehta | 2026-07-01 | Amber | 70% | 5 | OCR slow; NL-SQL late |  | Amber | 55% | 6 | RAG blocked; no API yet | MUST | 68 |  | Borderline — probe in debrief
Chidi Eze | solution/chidi | 2026-07-01 |  | S. Kaur | 2026-07-01 | Green | 100% | 12 | Ahead of pace |  | Green | 100% | 15 | Stretch: SPARQL + HITL done | Stretch | 91 |  | Strong hire
(consultant 1)
(consultant 2)
(consultant 3)
(consultant 4)
(consultant 5)
(consultant 6)

## Milestone Matrix
Milestone Matrix — capability progress per consultant
Status dropdown: Done / WIP / Blocked / Not started. '% done' row computes automatically. Example columns are shaded.
Milestone | Wk | Tier | Alice Okafor | Bob Nguyen | Chidi Eze | (consultant 1) | (consultant 2) | (consultant 3) | (consultant 4) | (consultant 5) | (consultant 6)
Env & stack (compose + seed healthy) | W1 | MUST | Done | Done | Done
OCR extraction (multi-page, skew, handwriting) | W1 | MUST | Done | Done | Done
Load -> Postgres + pgvector | W1 | MUST | Done | Done | Done
NL-to-SQL (schema-link + generate + validate) | W1 | MUST | Done | Done | Done
LangGraph orchestration (>=10 nodes) | W1 | MUST | Done | WIP | Done
RAG + reranker (nDCG lift) | W2 | Target | Done | Blocked | Done
ML underwriting (LightGBM + SHAP, AUC) | W2 | Target | Done | Not started | Done
HTMX app + auth + Postgres sessions + logging | W2 | Target | Done | Done | Done
Redis API (contract, cache, streams, k6) | W2 | Target | WIP | Not started | Done
SPARQL / ontology + HITL | W2 | Stretch | Not started | Not started | Done
Security/red-team + ADRs + demo | W2 | - | WIP | Not started | Done
% Done

## Weekly Checklist
Weekly milestones — what 'on track' means
Mirrors challenge-wbs.xlsx. Week 1 clears MUST; Week 2 reaches Target (Stretch = standout).
Week | Days | Expected milestones | Tier
Week 1 | D1-2 | Stack up (compose+seed); OCR detection + deskew | MUST
Week 1 | D3-4 | OCR structure + cursive + stitch; load to Postgres + pgvector | MUST
Week 1 | D5-7 | NL-to-SQL (link+generate+validate+execute); LangGraph SQL slice E2E | MUST
Week 2 | D8-9 | RAG + reranker (nDCG lift); LightGBM underwriting (AUC + reasons) | Target
Week 2 | D10-11 | Agents breadth (>=10 nodes); HTMX chat wired to graph (SSE) | Target
Week 2 | D12 | Redis API: endpoints, cache, rate-limit, idempotency, streams; k6 | Target
Week 2 | D13 | SPARQL lane + HITL + policy/compliance; load-test + tune | Stretch
Week 2 | D14 | Security/red-team, ADRs, README, demo, final scorecard + PR | -

## Dashboard
Cohort Dashboard
Metric | Value
Consultants tracked
On track (W2 Green)
At risk (W2 Amber)
Behind (W2 Red)
Passing (score >= 70)
Average score
Reached Stretch
W2 status | Count
Green
Amber
Red

## How to use
How to use this tracker
This workbook ships with 3 EXAMPLE consultants (shaded rows/columns) so you can see it populated.
Delete or overwrite them with your real cohort.
WEEKLY (twice, end of each week):
1. From the repo root: git fetch --all --prune
2. Auto-pull activity: python grading-kit/harness/consultant_status.py --start <cohort-start> --csv status.csv
-> Week-1 vs Week-2 commits, ahead count, last activity, PR+CI, and a grading-kit tamper flag.
3. 'Weekly Status' tab: one row per consultant. Paste commit counts; set W1/W2 RAG (Green/Amber/Red),
% complete, and notes. 'Due' and 'Pass?' compute automatically.
4. 'Milestone Matrix' tab: set each capability to Done / WIP / Blocked / Not started per consultant.
The '% Done' row and the cell colours update automatically. This is the granular progress view.
5. 'Weekly Checklist' tab tells you what 'on track' means each week (Week 1 = MUST, Week 2 = Target+).
FINAL (end of 14 days):
6. Run the grader (see grading-kit/RUNBOOK.md): docker compose up -> harness/scorer.py -> scorecard.json.
7. Enter Tier reached + Score /100 on 'Weekly Status'. Pass? computes (>=70).
8. 'Dashboard' rolls up the cohort (on-track / at-risk / behind, passing, average score).