## Candidate WBS
Candidate WBS — AutoLoan-DocIntel Take-Home (2h/day × 14 days = 28h)
Vertical-slice-first. Tiers: MUST (pass floor) · Target (strong) · Stretch (top of pool). Heavy data/infra is author-provided.
WBS | Day | Part | Task | Tier | Depends | Deliverable | Hrs | Cum
0.1 | D1 | Setup | Setup: clone, docker compose up, pull Ollama models, read API contract / schema / catalog, run stubs end-to-end | — | — | Running stack + orientation | 2
1.1 | D2 | OCR | OCR table detection + deskew/perspective-correct (TATR) on auto-loan forms | MUST | 0.1 | Detected table regions | 2
1.2 | D3 | OCR | OCR structure→grid JSON + cursive handwriting (TrOCR) + multi-page stitch; run ocr-eval | MUST/Stretch | 1.1 | Extractions + TEDS/CER | 2
1.3 | D4 | Integration | Load extractions → Postgres tables + chunk embeddings → pgvector | MUST | 1.2 | Populated DB + vector index | 2
2.1 | D5 | NL2SQL | Schema-linking via OpenMetadata + pgvector → minimal sub-schema | MUST | 1.3 | Sub-schema selector | 2
2.2 | D6 | NL2SQL | Qwen2.5-coder SQL gen + sqlglot validate + read-only execute + repair loop; run sql-eval | MUST | 2.1 | Execution-accuracy report | 2
3.1 | D7 | Orchestration | LangGraph core: router→linker→nl2sql→validator→executor→explainer + Redis checkpointer | MUST | 2.2 | Working SQL graph | 2
4.1 | D8 | RAG | Table-aware chunking + hybrid retrieval (BM25+dense, RRF) + bge-reranker; before/after nDCG; citations | Target | 3.1 | Reranked cited answers | 2
5.1 | D9 | ML | Train LightGBM PD model + SHAP→adverse-action reasons; expose as tool; report AUC | Target | 1.3 | Underwriting scorer tool | 2
3.2 | D10 | Orchestration | Agents breadth: +vector_retriever, reranker, underwriting, aggregator_critic (≥10 nodes wired) | Target | 4.1; 5.1 | ≥10-node graph | 2
6.1 | D11 | App | HTMX wiring: chat console → graph (SSE), document viewer overlay, underwriting panel | Target | 3.2 | Working UI | 2
7.1 | D12 | API | Redis API: contract endpoints, semantic cache, rate-limit, idempotency, Streams ingestion; k6 smoke | Target | 3.2 | Scalable API | 2
8.1 | D13 | Stretch | SPARQL/ontology lane + HITL interrupt/resume + policy/compliance; full k6 load test + tune | Stretch | 7.1 | Stretch features + load report | 2
9.1 | D14 | Cross-cut | Security/red-team (injection, secrets, SCA) + ADRs + README + demo + final scorecard | — | all | Submission package | 2
TOTAL

## Author Prep WBS
Author Prep WBS — building the challenge pack + grading kit (~2h tasks)
What Aelum does to produce the substrate candidates build on. ~36h total.
ID | Track | Task | Output | Hrs | Cum
A1 | docgen | HTML/Pillow form templates for 3 doc classes (application / verification / policy) | Form templates render | 2
A2 | docgen | Rasterize 300 DPI + Albumentations skew/perspective/noise with recorded homography | Distorted PNGs + meta.json | 2
A3 | docgen | Cursive handwriting overlay (SIL-OFL fonts) into signature/initial/margin regions | Handwritten layers composited | 2
A4 | docgen | Ground-truth emitters: grid-matrix JSON + PubTabNet-style HTML | Table GT per page | 2
A5 | docgen | hOCR/ALTO text GT + stitch.json + manifest.jsonl; 80/20 split + leakage guards + SHA256SUMS | Full label set + withheld test | 2
A6 | schema | 10 core auto-loan DDL tables hand-authored | db/ddl/10..40_*.sql | 2
A7 | schema | Templated dim/history/xref expansion to ≥100 tables / ≥200 cols + count self-check | Full schema | 2
A8 | schema | pgvector tables (doc/row embeddings, HNSW) + analytics views (90_views.sql) | Vector schema + views | 2
A9 | seed | Faker seed (referentially consistent; 12 docs↔example images) + fixed dump | seed.py + seed_fixed.sql.gz | 2
A10 | app | FastAPI shell: factory, config, async SQLAlchemy, structlog JSON + request/correlation middleware | Running skeleton | 2
A11 | app | Auth: argon2 + OAuth2 password flow + Postgres-backed session middleware | Login/logout works | 2
A12 | app | HTMX templates: login, chat (SSE canned), document viewer, underwriting, catalog | Pages render | 2
A13 | infra | docker-compose: postgres+pgvector, redis, ollama (+model-pull), app + healthchecks | compose up green | 2
A14 | catalog | OpenMetadata compose (MySQL+OpenSearch) + Postgres connector + page-index ingestion | Catalog populated | 2
A15 | grading | Harness: data-integrity + schema-conformance checks → scorecard.json | pytest suite | 2
A16 | grading | Harness: auth/session correctness + reproducibility/leakage checks | Suite complete | 2
A17 | grading | Reference-solution pass + rubric calibration + RUNBOOK | Solvable + scored | 2
A18 | docs | README brief, SUBMISSION.md, license/SHA manifest, clean-machine repro dry-run | Publishable pack | 2
TOTAL

## Rubric
Evaluation Rubric — 100 points (pass = 70)
Auto = computed by grading harness (scorecard.json). Manual = reviewer against anchors. Each line scored 0–5, normalized to weight.
Category | Scoring | Points | Anchor / what earns full marks
NL-to-SQL | Auto | 16 | Execution Accuracy (primary), Exact-Set-Match, valid-SQL rate, repair-loop count
OCR extraction | Auto | 14 | TEDS-Struct, GriTS-Top/Con, cell-F1, CER/WER (print vs handwriting), multi-page stitch F1
LangGraph orchestration | Manual | 14 | ≥10 nodes wired, route accuracy, Redis checkpointer, HITL interrupt/resume
RAG + reranker | Auto | 10 | Recall@40/MRR/nDCG@10 before vs after rerank; RAGAS faithfulness >0.70
App: HTMX + auth + sessions + logging | Auto/Manual | 10 | argon2 hashing, Postgres-backed sessions, JSON logs w/ request_id + correlation_id
Redis-scalable API | Auto | 10 | Contract conformance; semantic cache, rate-limit, idempotency, Streams ingestion; k6 SLOs
ML underwriting | Auto | 8 | AUC-ROC, PR-AUC, Brier (calibration), decision-agreement %, SHAP reason codes
Engineering quality | Manual | 8 | Tests (≥60% core), reproducible docker compose, CI, clean structure
SPARQL / ontology (Stretch) | Auto | 4 | Result-set F1 vs gold; valid-query rate over Oxigraph
Security & red-team | Manual | 4 | Prompt-injection defense, no secrets in repo, SCA/supply-chain, PII handling
Docs / ADRs / demo | Manual | 2 | README clarity, ≥3 ADRs explaining 'why', demo walkthrough
TOTAL |  |  | Pass threshold: 70 / 100

## Summary
Summary & Rollup
Effort totals
Candidate effort (hrs)
Author prep effort (hrs)
Candidate calendar (days @2h)
Rubric total (pts)
Pass threshold (pts) | 70
Candidate hours by part |  | Tier targets
Part | Hrs | MUST | OCR baseline (TEDS-Struct ≥0.70); SQL vertical slice ≥60% Exec-Acc; graph runs; auth/session/logging; /chat+/search
Setup |  | Target | RAG+rerank (nDCG lift, RAGAS>0.70); LightGBM AUC; ≥10 nodes; HTMX wired; Redis cache/limit/Streams; k6 @50 RPS
OCR |  | Stretch | SPARQL lane; HITL; policy/compliance; critic retry; full 14-node fan-out; handwriting CER≤0.15; Azure deploy
Integration
NL2SQL
Orchestration
RAG
ML
App
API
Stretch
Cross-cut
TOTAL